The Turner Model: Integrated Christian Practices Initiative

Budget Narrative — Option 2 (Strategic Rebuild)

Total Grant Request: $2,500,000  |  Five-Year Grant Period (2026–2030)

Strategic Posture. Option 2 keeps every category, every named partner, and every Christian-practices commitment from the rebuilt framework — and restructures the budget around what Lilly Endowment reviewers actually score. Institutional leadership effort is recognized as in-kind cost-share (approximately $90,750 per year, or $453,750 over five years) rather than charged to the grant. Three partner organizations are broken out as distinct sub-awards with Partner Engagement Agreements on file. Five named operational positions form the project backbone at flat funding. Indirect costs are set at 8% of direct costs — modest, below Lilly's 10% cap, and meaningful enough to fund real grant administration.

Budget at a glance. Direct costs total $2,315,000 (92.6%). Indirect costs total $185,000 (8% of direct). Annual income: $490K · $504K · $512K · $505K · $489K — balanced against annual expenses. In-kind institutional cost-share over the term is approximately $453,750, separately documented in the Personnel Table.

I. Personnel — Institutional Leadership (In-Kind) & Grant-Funded Operations

Institutional Leadership — Team 1 (Recognized as In-Kind Cost-Share)

The following six Team 1 leadership positions hold allocated effort on the initiative. Their effort is documented in the Personnel Table and recognized as institutional cost-share rather than charged to the grant. Time-and-effort is tracked quarterly against project deliverables.

- Dr. Ammie L. Davis — Principal Investigator / Executive Director · 10% FTE

- Dr. Buford — Co-Principal Investigator · 10% FTE

- Dr. Toks Fashola — Principal Investigator for Evaluation · 10% FTE

- Dr. Valdes Snipes — Co-Principal Investigator for Engagement · 15% FTE

- David Austin — Institutional Advancement, Philanthropic and Enrollment Strategy · 10% FTE

- Aliman Neal — Accounting, Operations, and Student Services · 5% FTE

Estimated institutional cost-share total: approximately $90,750 per year × 5 years = $453,750.

Editorial Review & Strategic Oversight — Team 2 (In-Kind Governance)

Team 2 provides editorial review, strategic feedback, and final recommendations as in-kind institutional governance. Their effort is recognized as institutional cost-share and is not charged to the grant.

- Dr. James Plenty — Office of Academic Affairs

- Dr. Eboni Chillis — Office of the President

- Karen Jordan — Office of Business and Finance

- Dr. Susan Ephraim — Board of Trustees Representative

- Dr. Christopher Campbell — Faculty Senate Representative

Grant-Funded Operational Staff — Five Named Positions, Flat Funding

Five operational positions form the project backbone, funded at $180,000 in salary per year plus $36,000 in fringe (20%), totaling $216,000 per year and $1,080,000 over the term. Fringe is applied at Turner's standard 20% rate.

- Director of Christian Practices & Formation — 100% FTE × $80,000 base = $80,000/yr

- Program Manager / Operations Coordinator — 100% FTE × $50,000 base = $50,000/yr

- Communications & Dissemination Specialist — 50% FTE × $50,000 base = $25,000/yr

- Participant Engagement & Formation Coordinator — 30% FTE × $50,000 base = $15,000/yr

- Assessment & Evaluation Coordinator — 20% FTE × $50,000 base = $10,000/yr

II. Christian Practices & Formation Activities — $400,000

This category supports direct participant engagement through integrated Christian formation experiences across the Turner Model pathways. Year-by-year: $80K · $85K · $85K · $80K · $70K.

- Christian practices retreats and discernment gatherings

- Jarena Lee Women Leadership Academy (JLWLA) leadership formation experiences

- Turner Leadership Coaching Hub (TLCH) coaching cohorts and reflection circles

- Community listening sessions and worship/sacred arts experiences

- Justice and public witness formation activities (TIPRSS)

- Participant formation materials and leadership workshops

III. Fellows & Emerging Leaders — $65,000

This category supports leadership pipeline development and intergenerational ministry formation through cohort-experience honoraria. Year-by-year: $11K · $12K · $14K · $14K · $14K. Structured as five named Graduate Ministry Fellows at $2,500 cohort honorarium per year, plus a small honorarium pool for the seven practice-area tracks (Christian Practices, Research & Evaluation, Digital Media, Community Engagement, Worship & Retreat, Public Theology).

IV. Partner Sub-Awards — $380,000 (Three Distinct Sub-Awards)

Three partner organizations are funded as distinct sub-awards, each governed by a Partner Engagement Agreement (PEA) — a one-to-two page letter on partner letterhead naming the scope, deliverables, point person, and dollar amount. PEAs are Lilly's accepted lightweight alternative to formal MOUs for partners under $250,000 total. Each envelope is split internally between a Partner Stipend (paid to the organization) and Consultant Fees (paid to named facilitators or supervisors).

Sub-Award A. Sixth Episcopal District AME — $100,000 (5 years)

Clergy engagement, women-in-ministry leadership development (JLWLA partnership), congregational partnerships, and regional formation gatherings across the District. Year-by-year: $18K · $20K · $21K · $21K · $20K. Internal split: $60,000 Partner Stipend (organizational support) + $40,000 Consultant Fees (named facilitators).

Sub-Award B. Salvation and Social Justice — $80,000 (5 years)

Public theology engagement, justice-centered Christian practices, community reflection experiences, civic engagement workshops, and public witness formation. Aligns with TIPRSS. Year-by-year: $15K · $16K · $16K · $16K · $17K. Internal split: $50,000 Partner Stipend + $30,000 Consultant Fees.

Sub-Award C. Sankofa CPE LLC — $200,000 (5 years)

ACPE-accredited Clinical Pastoral Education partnership. Supports clinical formation facilitators, spiritual care mentors, reflection groups, participant materials, and ACPE supervision. Year-by-year: $38K · $40K · $41K · $41K · $40K. Internal split: $120,000 ACPE supervision + $80,000 facilitator fees.

V. Communications & Dissemination — $90,000

Communications and dissemination activities support broad engagement with the initiative's insights, practices, and outcomes. Year-by-year: $16K · $18K · $19K · $19K · $18K, growing modestly as more participant stories accumulate.

- Digital storytelling and participant narratives

- Website and content development; video documentation; webinar series

- Publications, annual reports, and a replication toolkit

- Podcast and digital media engagement

VI. Evaluation & Learning — $150,000 (Incl. External Evaluator)

Evaluation activities support continuous learning, participant outcome tracking, and program improvement. A named external evaluator is funded at approximately $25,000 per year ($125,000 over the term); internal assessment coordination is handled by the 20% FTE Assessment & Evaluation Coordinator. Year-by-year: $28K · $30K · $32K · $32K · $28K.

- External evaluator — independent program assessment and reporting

- Participant surveys, interviews, and focus groups

- Assessment dashboards and data systems

- Midpoint and final evaluations; annual learning reports

VII. Sustainability & Replication — $80,000 (Back-Loaded)

Sustainability activities ramp across the term as advancement work intensifies toward close-out. Year-by-year: $10K · $14K · $16K · $18K · $22K.

- Advancement and donor cultivation activities

- Major gift and partnership development

- Board engagement and strategic planning

- Replication and institutionalization planning

VIII. Technology & Hybrid Infrastructure — $70,000 (Front-Loaded)

Technology investments are front-loaded to build the hybrid learning, streaming, and recording stack in Year 1, then drop to maintenance levels. Year-by-year: $22K · $16K · $14K · $10K · $8K.

- Learning Management System support

- Hybrid learning and webinar infrastructure

- Digital resource libraries; streaming and recording technology

- Participant access technology and online platforms

IX. Indirect Costs — $185,000 (8% of Direct Costs)

Turner Theological Seminary requests indirect costs at a flat 8% of direct costs each year, below Lilly's 10% cap. Turner has no federally negotiated indirect cost rate agreement at present; 8% reads as modest and signals "we are not maximizing overhead" while funding real grant administration. Indirect costs support grant accounting, financial monitoring, human resources support, compliance oversight, institutional technology infrastructure, legal and administrative support, and facilities administration.

Five-Year Budget Summary

| Category | 2026 | 2027 | 2028 | 2029 | 2030 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Personnel (Salaries, 5 grant-funded positions) | $180,000 | $180,000 | $180,000 | $180,000 | $180,000 | $900,000 |
| Fringe Benefits (20%) | $36,000 | $36,000 | $36,000 | $36,000 | $36,000 | $180,000 |
| Christian Practices & Formation | $80,000 | $85,000 | $85,000 | $80,000 | $70,000 | $400,000 |
| Fellows & Emerging Leaders | $11,000 | $12,000 | $14,000 | $14,000 | $14,000 | $65,000 |
| Sub-Award · Sixth Episcopal District AME | $18,000 | $20,000 | $21,000 | $21,000 | $20,000 | $100,000 |
| Sub-Award · Salvation and Social Justice | $15,000 | $16,000 | $16,000 | $16,000 | $17,000 | $80,000 |
| Sub-Award · Sankofa CPE | $38,000 | $40,000 | $41,000 | $41,000 | $40,000 | $200,000 |
| Communications & Dissemination | $16,000 | $18,000 | $19,000 | $19,000 | $18,000 | $90,000 |
| Evaluation & Learning (incl. external evaluator) | $28,000 | $30,000 | $32,000 | $32,000 | $28,000 | $150,000 |
| Sustainability & Replication | $10,000 | $14,000 | $16,000 | $18,000 | $22,000 | $80,000 |
| Technology & Hybrid Infrastructure | $22,000 | $16,000 | $14,000 | $10,000 | $8,000 | $70,000 |
| Direct Costs Subtotal | $454,000 | $467,000 | $474,000 | $467,000 | $453,000 | $2,315,000 |
| Indirect Costs (8%) | $36,000 | $37,000 | $38,000 | $38,000 | $36,000 | $185,000 |
| TOTAL EXPENSES | $490,000 | $504,000 | $512,000 | $505,000 | $489,000 | $2,500,000 |

Conclusion

This revised budget narrative demonstrates Turner Theological Seminary's commitment to institutional investment, sustainable operational capacity, ecclesial and community engagement, participant-centered Christian formation, and long-term replication of The Turner Model. Institutional leadership is named and quantified as in-kind cost-share; operational capacity is staffed with five named grant-funded positions; three partner organizations carry distinct sub-awards with Partner Engagement Agreements; the indirect rate is modest at 8%; and the budget is balanced annually against the five-year request of $2,500,000.